## Sheet1
Team Scorpion
Developers: B M M Bari - 1711384042 [ CSE327 Section 07 ] Aminul Islam Joy - 1711867642 [ CSE327 Section 07 ] Rafiul Hasan - 1712524042 [ CSE327 Section 07 ]
"House Rental and Management System"
Sprint Backlog: 02
ID | User Story | Tasks | Day 01 | Day 02 | Day 03 | Day 04 | Day 05 | Day 06 | Day 07
3 | As a user I want to be able to collect the utility bill so I don't have to keep tracks on the bills manually. | Design user interface for Utility Bill page | 5 | 0 | 0 | 0 | 0 | 0 | 0
|  | write code for Utility Bill page | 0 | 6 | 0 | 0 | 0 | 0 | 0
|  | Create database table for storing information | 0 | 0 | 3 | 2 | 0 | 0 | 0
|  | Connect Utility Bill page with database | 0 | 0 | 0 | 0 | 3 | 0 | 0
|  | Test the Utility Bill page | 0 | 0 | 0 | 0 | 0 | 1 | 0
4 | As a user I want to be able to Update or Delete informations so that I can keep the perfect calculation. | Write code for query and delete option | 0 | 1 | 0 | 1 | 0 | 1 | 0
|  | Run a test for delete option | 0 | 0 | 0 | 0 | 0 | 1 | 0